## Working route
Blackboard Group No ?? Class XYY | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update cell E3 to your PM class date | =====> | 2024-03-26 | Monday Mar.25 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 22 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each Team member | Priscilla Lacerda -Team Leader: Main function&code Kiet dung Truong- Team member: Converting Isaac Su -Team member -Fundamentals Yat Hei Wong -Team member: Tokenizing Fatemeh Ansari -Team member: Manipulations | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files | Realistic planned hours: 0.5hr actual hours: 0.5hr | Wednesday Mar.27 | TO DO | Yat Hei Wong did not finish his part-Tokenizing | 1.Deliverables are measured through Priscilla Lacerda's assembly of everyone's files, the creation of a GitHub repository for final file upload, and the subsequent upload of files to Blackboard. This process ensures that all necessary materials are compiled and accessible for assessment. 2.The delivery criteria have been agreed upon through the establishment of a WhatsApp group for discussion and file sharing. This platform serves as a means for communication and collaboration, facilitating the exchange of ideas and materials essential for project completion. 3.Priscilla Lacerda has initiated the timeline setup by providing the necessary code on March, 29th. Additionally, a clear timeline has been established wherein each member is required to submit their respective parts one day before the due date. This timeframe allows Priscilla Lacerda ample time to organize the submissions and ensure timely completion of the project. | 1/1 | see Project Milestones and Details |  | Everyone has completed their part on time. We discussed together and learned how to use git. | We measured the deliverable by consulting with the professor at school to understand how to write the project plan. Through this consultation, we clarified and agreed upon the delivery criteria. | 1/1 | see Project Milestones and Details |  | Everyone has completed their part on time. We discussed together and learned how to use git. | We measured the deliverable by consulting with the professor at school to understand how to write the project plan. Through this consultation, we clarified and agreed upon the delivery criteria. | 1/1 | see Project Milestones and Details
Team Meeting Agenda ==> | Assign tasks to each member, ensuring they have clear responsibilities and providing a timeline for completion | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | Realistic planned hours: 1.5hrs actual hours: 1hr | Thursday Mar.28 | TO DO | Each member spent a lot of time reading the final project instructions and also expended significant effort in locating all the necessary resources. | 1. Deliverable Measurement and Criteria Agreement 2. Timeline Setup 3. Task Assignment and Responsibilities 4. Communication Channels 5. Progress Tracking and Reporting 6. Next Steps and Action Items | 2/2 | Monday Apr.1 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | 1. Deliverable Measurement and Criteria Agreement 2. Timeline Setup 3. Task Assignment and Responsibilities 4. Communication Channels 5. Progress Tracking and Reporting 6. Next Steps and Action Items | 2/2 | Wednesday Dec.14 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 2/2 | Wednesday Dec.14 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. | updated all DONE items with actual hours. | Monday Dec.12 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." | N/A | Friday Mar.29 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Apr.1 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Saturday Apr.6 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Sunday Apr.14 | TO DO
[Isaac Su] Fundamentals | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  | Realistic planned hours: 1.5 hrs actual hours: 1.5hrs | Thursday Mar.28 | DONE | test the module of V1 and provide the required files | Finish commenting, running and testing the code by several test cases. Uploaded the required four files. |  | Tuesday Apr.2 | DONE | test the module of V2 and provide the required files | Complete the task of integrating version 2 requirements into version 1 files. Ensure all changes are properly added, committed, and logged in Git for version 2. Finally, share the updated files with the team leader on Teams for their review and feedback. |  | Sunday Apr.7 | DONE | test the module of V3 and provide the required files | Complete the task of enhancing the code by adding comments, compiling it, and performing thorough testing. After ensuring everything works as expected, commit the changes to the Git repository for version 3. Finally, share the updated files with the team leader on Teams and request their review and feedback. |  | Monday Apr.15 | DONE |  |  |  | Tuesday Dec.13
[Fatemeh Ansari ] Manipulations | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  | Realistic planned hours: 0.5 hrs actual hours: 0.5hrs | Thursday Mar.28 | DONE | test the module of V1 and provide the required files | Finish commenting, running and testing the code by several test cases. Uploaded the required four files. |  | Tuesday Apr.2 | DONE | test the module of V2 and provide the required files | Fatemeh Ansari did not complete her part, and its was made by Kiet Dung Truong |  | Sunday Apr.7 | DONE | test the module of V3 and provide the required files | Fatemeh Ansari did not complete her part, and its was made by Kiet Dung Truong |  | Monday Apr.15 | DONE |  |  |  | Tuesday Dec.13
[Yat Hei Wong] Tokenizing | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  | Realistic planned hours: 0.5 hrs actual hours: 0.5hrs | Thursday Mar.28 | DONE | test the module of V1 and provide the required files | Yar Hei (Lawrence) Wong did not complete his part, and its was made by Priscilla Lacerda |  | Tuesday Apr.2 | DONE | test the module of V2 and provide the required files | Complete the task of integrating version 2 requirements into version 1 files. Ensure all changes are properly added, committed, and logged in Git for version 2. Finally, share the updated files with the team leader on Teams for their review and feedback. |  | Sunday Apr.7 | DONE | test the module of V3 and provide the required files | Yat Hei Wong (Lawrence) did not complete his part, and it was made by Issac |  | Monday Apr.15 | DONE |  |  |  | Tuesday Dec.13
[Priscilla Lacerda/ Kiet dung Truong] Conversions Team Leader | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader |  | Realistic planned hours: 3 hrs actual hours: 3hrs | Friday Mar.29 | DONE | test the module of V1 and provide the required files | Finish commenting, running and testing the code by several test cases. Uploaded the required four files. |  | Wednesday Apr.3 | DONE | test the module of V2 and provide the required files | Complete the task of integrating version 2 requirements into version 1 files. Ensure all changes are properly added, committed, and logged in Git for version 2. Finally, share the updated files with the team leader on Teams for their review and feedback. |  | Monday Apr.8 | DONE | test the module of V3 and provide the required files | Complete the task of enhancing the code by adding comments, compiling it, and performing thorough testing. After ensuring everything works as expected, commit the changes to the Git repository for version 3. Finally, share the updated files with the team leader on Teams and request their review and feedback. |  | Tuesday Apr.16 | DONE |  |  |  | Wednesday Dec.14
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.